## Cover
SYSTEM TEST CASE
Project Name | Electric Store |  |  | Creator | TRAN CHI DO
Project Code | SEP490 |  |  | Reviewer/Approver | QUACH DANG KHOA
Document Code | SEP490_02_Report5_Test Case Document |  |  | Issue Date | 2024-07-14
|  |  |  | Version | 1.0.0
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2024-07-02 | 1.0.0 | All | A | Initial version
2024-07-02 | 1.0.0 |  | A | Add features 13, 14, 15, 16, 17
2024-07-05 | 1.0.0 |  | A | Modifier Features

## Test case List
TEST CASE LIST
Project Name |  | Electric Store
Project Code |  | SEP490
Test Environment Setup Description |  | List enviroment requires in this system 1. Server 2. Database 3. Web Browser
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Sign in | Authentication |  | Account must exist
2 | Sign up | Authentication |  | The user must have a valid Google account to sign up.
3 | Sign out | Authentication |  | Account must exist, user must login first
4 | View all products | View
5 | View product detail | View
6 | View orders history | View |  | Account must exist, user must login first
7 | View all blogs | View
8 | Suggestion and search by keyword | View
9 | Recommendations by behavior | View
10 | Manage Cart | User Management
11 | Check out | Payment |  | Account must exist, user must login first
12 | Feedback | Product Feedback | Allows Customers to provide feedback on products | Customer must have purchased the product
13 | Rating | Product Feedback | Allows customers to rate products | Customer must have purchased the product
14 | Filter | View | Allows users to filter products based on various criteria | Products must exist in the database
15 | Manage Profile (RU) | User Management | Allows users to read and update their profile information | User must be signed in
16 | Manage Blogs (CRUD) | Blog Management | Allows admin to create, read, update, and delete blogs | Admin privileges required
17 | Manage Orders (RU) | Order Management | Allows admin to read and update order statuses | Admin privileges required
18 | Manage Product (CRUD) | Product Management | Allows admin to create, read, update, and delete products | Admin privileges required
19 | Manage Staff (CRUD) | Staff Management | Allows admin to manage staff information | Admin privileges required
20 | Manage Customer (R) | User Management | Allows admin to view customer information | Admin privileges required
21 | Dashboard Statistics | View | Displays various statistics on the dashboard
22 | Export File | View | Allows exporting of data to Excel files | Data to be exported must exist
23 | Manage Category (CRUD) | Category Management | Allows admin to manage product categories | Admin privileges required
24
25
26
27
28
29
30
31
32
33
34
35

## Category Management
Feature | <Category Management> | [7 empty] | Pass
Test requirement | <> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
3 | 0 | 0 | 0 | 3
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Manage Category (CRUD)
MCr-01 | Verify whether the admin can create new product categories. | 1. Sign in using administrator login information. 2. Navigate to the "Category management" section on the navigation bar. 3. Click the "New category" button. 4. Enter a valid category name. 5. Save the new category. | The new category will be created and displayed in the category list. | Administrator is sign in. | Pass | 2024-07-14 | Tran Chi Do
MCr-02 | Verify whether the admin can update the name of an existing category. | 1. Sign in using administrator login information. 2. Navigate to the "Category management" section on the navigation bar. 3. Click the Name field of the category to update. 4. Modify the category name 5. Click the "Update" button to prioritize the newly changed category. | Category names must be updated and reflected in the category list. | Administrator is logged in. There are existing categories in the database. | Pass | 2024-07-14 | Tran Chi Do
MCr-03 | Verify whether the admin can delete an existing category. | 1. Sign in using administrator login information. 2. Navigate to the "Category management" section on the navigation bar. 3. Click the Name field of the category to delete. 4.Click "Delete"l button to delete the category. 5. Confirm deletion. | The selected category will be deleted and no longer appear in the category list. | Administrator is logged in. There are existing categories in the database. | Pass | 2024-07-14 | Tran Chi Do

## View
Feature | <View> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
10 | 0 | 0 | 0 | 10
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Filter
F-01 | Verify if products can be filtered based on a single criterion (e.g. price). | 1. Log in to the Home page 2. Click "Shop" page 3. Click "Sort by" 4. Apply price range filter | Only products within the specified price range are displayed. | Products with different prices are available in the database. | Pass | 2024-07-12 | Tran Chi Do
F-02 | Ensure products can be filtered based on multiple criteria (e.g. category and price). | 1. Log in to the Home page 2. Click "Shop" page 3. Click "Sort by" or Click on each CATEGORIES on the right side of the screen: Electric Fan, Refrigerator, TV, Speaker, .... 4. Apply price and category range filter | Only products belonging to the selected category and within the specified price range will appear. | Products exist in different categories with various price ranges in the database. | Pass | 2024-07-12 | Tran Chi Do
F-03 | Evaluate filtering performance with large data sets. | 1. Log in to the Home page 2. Click "Shop" page 3. Click "Sort by" or Click on each CATEGORIES on the right side of the screen: Electric Fan, Refrigerator, TV, Speaker, ....e 4. Apply price and category range filter | Filters must be applied promptly and the page will load efficiently even with a large number of products. | A significant number of products are available in the database. | Pass | 2024-07-12 | Tran Chi Do
Recommendations by behavior
RC-01 | Product recommendations based on user behaviour | 1. Access the website. 2. Navigate from the home page to the "Shop" section. 3. Click on a specific product to view its detail page. 4. Scroll down to the recommendations section on the product detail page. | 1. The system should display a list of recommended products based on the user's behaviour, preferences, and shopping history below the product details. 2. The recommended products should be relevant and personalised to the user's actions. 3. The user should be able to interact with the recommended products (view details). |  | Pass | 2024-08-08 19:16 | Quach Dang Khoa
Suggestion and search by keyword
KW-01 | Search keyword | 1. Access the website. 2. Locate the search bar on the navigation bar. 3. Enter a keyword related to a product in the search bar. 4. Observe the suggestions that appear as you type. 5. Press "Enter" or click the search icon to initiate the search. | 1. As the user types a keyword, relevant product suggestions should appear below the search bar. 2. Upon pressing "Enter" or clicking the search icon, the user should be redirected to a search results page displaying products that match the keyword. | There must be products in the inventory that match the keywords used in the search. | Pass | 2024-08-08 19:16 | Quach Dang Khoa
View orders history
OH-01 | Function to display orders history | 1. Visit to the website 2. On the navigation bar, click "Sign in with google" 3. On the navigation bar, click on the "My Orders" link to navigate to the order history section. | 1. The user should be successfully logged in. 2. The user should be redirected to the "My Orders" section upon clicking the "My Orders" link on the navigation bar. 3.The order history page should display a list of all past orders, including order numbers, dates, statuses, and details of each order. | 1. The user must have an account and be logged in. 2. The user must have at least one completed order in their order history. | Pass | 2024-08-08 19:16 | Quach Dang Khoa
View product detail
DP-01 | Function to display product detail. | 1. Visit to the website 2. Navigate to the "Shop" section 3. In the shop section, click on a specific product to view its details. | 1. Successfully displayed all product |  | Pass | 2024-08-08 19:16 | Quach Dang Khoa
View all products
AP-01 | Function to display all product list. | 1. Visit to the website 2. Navigate to the "Shop" section | 1. Successfully displayed all product. |  | Pass | 2024-08-08 19:16 | Quach Dang Khoa
Dashboard Statistics
DS-01 | Verify if the dashboard displays overall sales statistics. | 1. Sign in using administrator login information. 2. Navigate to the "Admin dashboard" section on the navigation bar. 3. Observe the display of overall sales statistics. | The dashboard will display accurate and up-to-date overall sales statistics. | Administrator is logged in. There are sales records in the database. | Pass | 2024-07-14 | Tran Chi Do
Export File
EF-01 | Verify if the system allows exporting sales data to an Excel file. | 1. Sign in bằng thông tin xác thực người dùng phù hợp. 2. Điều hướng đến phần "Order manage " trên thanh điều hướng. 3. Nhấp vào nút "Xuất". | The Excel file containing sales data must be downloaded and saved correctly. | There are sales data records in the database. | Pass | 2024-07-14 | Tran Chi Do

## User Management
Feature | <User Management> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
10 | 0 | 0 | 0 | 10
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Manage Cart
MC-01 | Verify that both guests and customers can successfully add items to their shopping cart. | 1. Access the website. 2. On the navigation bar, select the "Shop" section. 3. Click on any product to view its details. 4. Select the quantity of the product. 5. Click on the "Add to Cart" button. | 1. The user is successfully redirected to the product detail page. 2. The user can select the desired quantity. 3. The system adds the selected item to the cart. 4. The cart is updated and the user can see the newly added item in the cart. | 1. The website must be live and accessible. 2. There must be products available in the inventory. 3. The "Add to Cart" functionality must be correctly configured and operational. | Pass | 2024-08-08 19:16
MC-02 | Verify that the system handles failures appropriately when guests and customers attempt to add items to their shopping cart. | 1. Access the website. 2. On the navigation bar, select the "Shop" section. 3. Click on any product to view its details. 4. Select the quantity of the product. 5. Click on the "Add to Cart" button. 6. Simulate an error while adding the item to the cart (e.g., server error, network issue). | 1. The system fails to add the selected item to the cart. 2. The cart contents remain unchanged and the item is not added to the cart. | 1. The website must be live and accessible. 2. There must be products available in the inventory. 3. The "Add to Cart" functionality must be correctly configured and operational. | Pass | 2024-08-08 19:16
MC-03 | Verify that users can successfully view all items in their shopping cart | 1. Access the website. 2. As a guest or logged-in user, select the cart icon from the navigation bar. 3. Observe the list of items displayed in the shopping cart. | 1. Display all product | 1. The website must be live and accessible. 2. There must be items added to the cart by the user. | Pass | 2024-08-08 19:16
MC-04 | Verify that the system handles failures appropriately when users attempt to view all items in their shopping cart. | 1. Access the website. 2. As a guest or logged-in user, select the cart icon or "View Cart" option from the navigation bar. 3. Simulate an error while retrieving the cart contents (e.g., server error, network issue). | 1. The system fails to retrieve and display the cart contents. 2. The cart are not updated or displayed. | 1. The website must be live and accessible. 2. There must be items added to the cart by the user.
MC-05 | Verify that guests can remove items from their shopping cart | 1. Access the website. 2. As a guest or logged-in user, select the cart icon from the navigation bar. 3. Select the option to remove an item from the cart. | 1. The system displays the current cart contents, including item names, quantities, and prices. 2. The system removes the selected item from the cart in session storage. 3. The system updates and displays the cart after the item is removed | 1. The system will display the products that the guest has added to the cart | Pass | 2024-08-08 19:16
MC-06 | Verify that the system handles failures appropriately when users attempt to remove items from their shopping cart. | 1. Access the website. 2. As a guest or logged-in user, navigate to the cart page. 3. Select the option to remove an item from the cart. Simulate an error while updating the cart (e.g., server error, network issue). | 1. The system fails to remove the selected item from the cart. 2. The cart contents remain unchanged and the item is still present in the cart. | 1. The website must be live and accessible. 2. There must be items added to the cart by the user. 3. The "Remove Item" functionality must be correctly configured and operational. | Pass | 2024-08-08 19:16
MC-07 | Verify that guests can successfully edit the quantity of items in their shopping cart. | 1. Access the website. 2. On the navigation bar, select the "Shop" section. 3. Click on any product to view its details. 3. Select the quantity of the product. 4. Click on the "Add to Cart" button. 5. Navigate to the cart page by clicking on the cart icon on the navigation bar. Increase or decrease the quantity of an item in the cart. Verify that the cart is updated with the new quantity. | 1. The user is successfully redirected to the product detail page. 2. The user can select the desired quantity. 3. The system adds the selected item to the cart. 4. The user is redirected to the cart page upon clicking the cart icon. 5. The user can increase or decrease the quantity of an item in the cart. 6.The cart is updated with the new quantity. | 1. The website must be live and accessible. 2. There must be products available in the inventory. 3. The "Add to Cart" and "Edit Cart" functionalities must be correctly configured and operational. | Pass | 2024-08-08 19:16
MC-08 | Verify that the system handles failures appropriately when guests attempt to edit the quantity of items in their shopping cart. | 1. Access the website. 2. On the navigation bar, select the "Shop" section. 3. Click on any product to view its details. 4. Select the quantity of the product. 5. Click on the "Add to Cart" button. 6. Navigate to the cart page by clicking on the cart icon on the navigation bar. 7. Attempt to increase or decrease the quantity of an item in the cart. 8. Simulate an error while updating the cart (e.g., server error, network issue). | 1. The system fails to update the quantity of the selected item in the cart. 2. The cart contents remain unchanged and the original quantity is still | 1. The website must be live and accessible. 2. There must be products available in the inventory. 3. The "Add to Cart" and "Edit Cart" functionalities must be correctly configured and operational. | Pass | 2024-08-08 19:16
Manage Profile (RU)
MP-01 | Verify if a signed-in user can view their profile information. | 1. Sign in with valid user credentials. 2. Click on the settings icon in the upper right corner of the screen. 3. Click on "Profile" 4. Display user information | The profile page will accurately display the user's current profile information. | User is signed in. The user has an existing profile with information stored in the database. | Pass | 2024-08-08 19:16
MP-02 | Make sure users can update their profile information. | 1. Sign in with valid user credentials. 2. Click on the settings icon in the upper right corner of the screen. 3. Click on "Profile" 4. Edit one or more fields (e.g. name, phone number, contact details.). 5. Save changes. | Updated profile information must be saved and displayed correctly. | User is logged in. The user has an existing profile with information stored in the database. | Pass | 2024-08-08 19:16
Manage Customer (R)
MCs-01 | Verify whether admin can see customer details or not. | 1. Sign in using administrator login information. 2. Go to the "Customer management" section on the navigation bar. 3. Click on the eye icon of an existing customer from the list to view their details. | The system will display all relevant details of the selected customer (ID, Full name, Email, Phone, Country, City, Address). | Administrator is logged in. There are existing customers in the database. | Pass

## Staff Management
Feature | <Staff Management> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
4 | 0 | 0 | 0 | 4
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Manage Staff (CRUD)
MS-01 | Verify whether admin can create new staff or not. | 1. Sign in using administrator login information. 2. Go to the "Staff management" section on the navigation bar. 3. Click "New staff." 4. Enter valid data in all required fields (name, email, password, confirm password). 5. Save new staff. | The new staff will be successfully created and displayed in the staff list. | Administrator is logged in. | Pass | 2024-08-08 19:16 | Tran Chi Do
MS-02 | Make sure admins can see staff details. | 1. Sign in using administrator login information. 2. Go to the "Staff management" section on the navigation bar. 3. Click on the email field of each existing staff member from the list to view their details. | The system will display all relevant details of the selected staff (name, email, password). | Administrator is logged in. There are existing staff in the database. | Pass | 2024-08-08 19:16 | Tran Chi Do
MS-03 | Verify whether the admin can update the details of existing staff. | 1. Sign in using administrator login information. 2. Go to the "Staff management" section on the navigation bar. 3. Click on the email field of each existing staff member from the list to edit. 4. Modify staff details (name, email, password). 5. Click "Update" to save the changes. | Staff details must be updated and accurately reflected in the staff roster. | Administrator is logged in. There are existing staff in the database. | Pass | 2024-08-08 19:16 | Tran Chi Do
MS-04 | Make sure the admin can delete an existing staff. | 1. Sign in using administrator login information. 2. Go to the "Staff management" section on the navigation bar. 3. Click on the email field of each existing staff member from the list to delete. 4. Click "Delete" to delete. 5. Confirm deletion. | The selected staff will be removed from the staff list. | Administrator is logged in. There are existing staff in the database. | Pass | 2024-08-08 19:16 | Tran Chi Do
MS-05

## Order Management
Feature | <Order Management> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
2 | 0 | 0 | 0 | 2
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Manage Orders (RU)
MO-01 | Verify whether admin can see order details or not. | 1. Sign in using administrator login information. 2. Go to "Order management". 3. Click "Payment ID" of an order from the list to view details | The system will display all relevant details of the selected order (e.g. items in the order, customer details, total amount). | Administrator is logged in. There are existing orders in the database. | Pass | 2024-08-08 19:16 | Tran Chi Do
MO-02 | Make sure admins can update the status of orders. | 1. Sign in using administrator login information. 2. Go to "Order management". 3. Click "Payment ID" of an order from the list to update its status. 4. Change order status: Click "Mark a Shipped" | Order status must be updated and accurately reflected in the order details. | Administrator is logged in. There are existing orders in the database. | Pass | 2024-08-08 19:16 | Tran Chi Do

## Product Management
Feature | <Product Management> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
5 | 0 | 0 | 0 | 5
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Manage Product (CRUD)
MP-01 | Verify whether the admin can create new products. | 1. Sign in using administrator login information. 2. Navigate to the "Product Management" section on the navigation bar. 3. Click "New product." 4. Enter valid data in all required fields (e.g. name, description, price, category). 5. Click the "Create" button to save the product. | The new product must be successfully created and displayed in the product list. |  | Pass | 2024-07-14 | Tran Chi Do
MP-02 | Make sure admins can see product details. | 1. Sign in using administrator login information. 2. Navigate to the "Product Management" section on the navigation bar. 3. Click on the "name" of an existing product from the list to view details. | The system will display all relevant details of the selected product (e.g. name, description, price, category). | Administrator is logged in. There are existing products in the database. | Pass | 2024-07-14 | Tran Chi Do
MP-03 | Verify whether an administrator can update an existing product. | 1. Sign in using administrator login information. 2. Navigate to the "Product Management" section on the navigation bar. 3. Click "name" of an existing product from the list to edit. 4. Modify product details (e.g. name, description, price, category). 5. Click the "Update" button to save product changes. | Product details must be updated and accurately reflected in the product listing. | Administrator is logged in. There are existing products in the database. | Pass | 2024-07-14 | Tran Chi Do
MP-04 | Ensure admins can delete existing products. | 1. Sign in using administrator login information. 2. Navigate to the "Product Management" section on the navigation bar. 3. Tap "name" an existing product from the list to delete. 4. Press the "Delete" button to delete the product. 5. Confirm deletion. | The selected product will be removed from the product list. |  | Pass | 2024-07-14 | Tran Chi Do
MP-05 | Check if the system validates required fields during product creation. | 1. Sign in using administrator login information. 2. Navigate to the "Product Management" section on the navigation bar. 3. Click "New product." 4. Try to save without entering data in required fields (e.g. name, price). 5. Click the "Create" button. | The system displays appropriate error messages for missing required fields and prevents saving. |  | Pass | 2024-07-14 | Tran Chi Do

## Blogs Management
Feature | <Blogs Management> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
5 | 0 | 0 | 0 | 5
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Manage Blogs (CRUD)
MB-01 | Verify whether the admin can create new blog posts. | 1. Sign in with administrator credentials. 2. Navigate to the blog management section. 3. Click "New blog." 4. Enter valid data in all required fields (e.g. title, content,...). 5. Save the blog post. | The new blog post will be successfully created and displayed in the blog list. | Administrator is sign in. | Pass | 2024-07-13 | Tran Chi Do
MB-02 | Make sure admins can see a specific blog post. | 1. Sign in with administrator credentials. 2. Navigate to the blog management section. 3. Select the title of an existing blog post from the list. | The selected blog post will be displayed with all its content. | Administrator is sign in. There are existing blog posts in the database. | Pass | 2024-07-13 | Tran Chi Do
MB-03 | Verify whether an admin can update an existing blog post. | 1. Sign in with administrator credentials. 2. Navigate to the blog management section. 3. Select the title of an existing blog post from the list to edit. 4. Modify content or other fields. 5. Save changes. | log posts should be updated with new information. | Administrator is signed in. There are existing blog posts in the database. | Pass | 2024-07-13 | Tran Chi Do
MB-04 | Make sure admins can delete existing blog posts. | 1. Log in with administrator credentials. 2. Navigate to the blog management section. 3. Select the title of an existing blog post from the list to delete. 4. Click the "Delete" button. 5. Confirm deletion. | The selected blog post will be removed from the list. | Administrator is sign in. There are existing blog posts in the database. | Pass | 2024-07-13 | Tran Chi Do
MB-05 | Check if the system validates required fields during blog post creation. | 1. Log in with administrator credentials. 2. Navigate to the blog management section. 3. Click "New blog" 4. Try to save without entering data in required fields (e.g. title, content). | The system displays appropriate error messages for missing required fields and prevents saving. | Administrator is sign in. | Pass | 2024-07-13 | Tran Chi Do

## Authentication
Feature | <Authentication> | [7 empty] | Pass
Test requirement | <This sheet is used to test the authorization and authentication features of the system. In addition, it also tests the user management features of the system.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
8 | 0 | 0 | 0 | 8
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Pass | Test date | Tester | Note
Login
LG-01 | Login test successful with admin or staff account | 1. Visit the website in super admin login page 2. Enter userName: admin 3. Enter password: admin 4. Click "Sign in with credentials" button | 1. Redirected to Dashboard | Account must exist and not be deactivated | Pass | 2024-07-01 | Quach Dang Khoa
LG-04 | Login test successful with customer account | 1. Visit the website 2. Click "Sign in with google" button | 1. Redirected to Dashboard | Account must exist and not be deactivated | Pass | 2024-07-01 | Quach Dang Khoa
LG-05 | Login test failed with admin or staff account: blank userName | 1. Visit the website in admin login page 2. Let bank userName 3. Enter password: admin 4. Click "Sign in with credentials" button | Receive error message "Sign in failed. Check the details you provided are correct." |  | Pass | 2024-07-01 | Quach Dang Khoa
LG-06 | Login test failed with admin and staff account: blank password | 1. Visit the website in admin login page 2. Enter userName: admin 3. Let bank Password 4. Click "Login" button | Receive error message "Sign in failed. Check the details you provided are correct." |  | Pass | 2024-07-01 | Quach Dang Khoa
LG-07 | Login test failed with admin staff account: incorrrect userName | 1. Visit the website in admin login page 2. Enter userName: ad@system 3. Enter password: admin 4. Click "Sign in with credentials" button | Receive error message "Sign in failed. Check the details you provided are correct." |  | Pass | 2024-07-01 | Quach Dang Khoa
LG-08 | Login test failed with admin staff account: incorrrect password | 1. Visit the website in admin login page 2. Enter userName: admin 3. Enter password: admin@123 4. Click "Sign in with credentials" button | Receive error message "Sign in failed. Check the details you provided are correct." |  | Pass | 2024-07-01 | Quach Dang Khoa
LG-08 | Login test failed with admin staff account: incorrrect password | 1. Visit the website in admin login page 2. Enter userName: admin 3. Enter password: admin@123 4. Click "Sign in with credentials" button | Receive error message "Sign in failed. Check the details you provided are correct." |  | Pass | 2024-01-07 | Quach Dang Khoa
Sign up
[6 empty] | 2024-01-07 | Quach Dang Khoa
Sign Out
SO-01 | Log out test successful | Click "Logout" link in navigation | 1. Redirected to homepage |  |  | 2024-01-07 | Quach Dang Khoa

## Product Feedback
Feature | <Product Feedback> | [7 empty] | Pass
Test requirement | <This sheet is used to test the authorization and authentication features of the system. In addition, it also tests the user management features of the system.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
2 | 0 | 0 | 0 | 2
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Feedback
PF-01 | Verify user can provide feedback on products | 1. Sign in 2. Navigate to My order 3. Select purchased product 4. Click "Feedback" button 5. Provide feedback | Customer can successfully submit feedback for purchased product | Customer must have purchased the product | Pass | 2024-07-11 | Tran Chi Do
Rating
PF-02 | Verify user can rate products | 1. Sign in 2. Navigate to My order 3. Select purchased product 4. Click "Feedback" button 5. Provide feedback | The customer was able to successfully submit a rating for the purchased product | Customer must have purchased the product | Pass | 2024-07-11 | Tran Chi Do

## Payment
Feature | <Payment> | [7 empty] | Pass
Test requirement | <This sheet is used to test the user role management feature. You must log in with admin privileges to use this feature.> | [7 empty] | Fail
Reference Document | [8 empty] | Untesed
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | N/A
2 | 0 | 0 | 0 | 2
ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Result | Test date | Tester | Note
Check out
CO-01 | Verify that customers can successfully check out using VN-Pay after logging in. | 1. Access the website. 2. Log in with a valid customer account. 3. Click on the cart icon on the navigation bar. 4. Click on the "Checkout" button. 5. Fill in the required information: Full Name, Phone, Address. 6. Select VN-Pay as the payment method. 7. Click on the "Pay" button. 8. Complete the VN-Pay payment process. 9. Verify that the system redirects to the payment success page. | 1. The user is successfully logged in. 2. The user is click the "cart" icon. 3. The user is redirected to the checkout page upon clicking the "Checkout" button. 4. The system accepts the entered Full Name, Phone, and Address. 5. The system processes the payment via VN-Pay. 6. The system redirects the user to the payment success page after successful payment. | 1. The website must be live and accessible. 2. The user must have a valid customer account. 3. The user must have items in the cart. 4. The VN-Pay payment gateway must be correctly configured and operational. | Pass | 2024-08-08 19:16 | Quach Dang Khoa
CO-02 | Verify that the system handles payment failures appropriately when customers attempt to check out using VN-Pay. | 1. Access the website. 2. Log in with a valid customer account. 3. Click on the cart icon on the navigation bar. 4. Click on the "Checkout" button. 5. Fill in the required information: Full Name, Phone, Address. 6. Select VN-Pay as the payment method. 7. Click on the "Pay" button. 8. Simulate a payment failure during the VN-Pay process (e.g., insufficient funds, network issue). 9. Verify that the system redirects to the payment failure page. | 1.The user is successfully logged in. 2. The user is redirected to the cart page upon clicking the cart icon. 3. The user is redirected to the checkout page upon clicking the "Checkout" button. 4. The system accepts the entered Full Name, Phone, and Address. 5. The system attempts to process the payment via VN-Pay. 6. The system detects the payment failure. 7. The system redirects the user to the payment failure page and displays an appropriate error message. | 1. The website must be live and accessible. 2. The user must have a valid customer account. 3. The user must have items in the cart. 4. The VN-Pay payment gateway must be correctly configured and operational. | Pass | 2024-08-08 19:16 | Quach Dang Khoa
2024-08-08 19:16
2024-08-08 19:16
2024-08-08 19:16
2024-08-08 19:16

## Test Report
TEST REPORT
Project Name | Electric Store |  | Creator |  |  | TRAN CHI DO
Project Code | electric-store |  | Reviewer/Approver |  |  | TRAN CHI DO
Document Code | SEP490_02_Report5_Test Case Document |  | Issue Date |  |  | 2024-08-07
Notes
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | <Product Feedback> | 2 | 0 | 0 | 0 | 2
2 | <Payment> | 2 | 0 | 0 | 0 | 2
3 | <Product Management> | 5 | 0 | 0 | 0 | 5
4 | <Staff Management> | 4 | 0 | 0 | 0 | 4
5 | <Authentication> | 8 | 0 | 0 | 0 | 8
6 | <View> | 10 | 0 | 0 | 0 | 10
7 | <User Management> | 10 | 0 | 0 | 0 | 10
8 | <Order Management> | 2 | 0 | 0 | 0 | 2
9 | <Category Management> | 3 | 0 | 0 | 0 | 3
10 | <Blogs Management> | 5 | 0 | 0 | 0 | 5
| Sub total | 51 | 0 | 0 | 0 | 51
| Test coverage |  | 100 | %
| Test successful coverage |  | 100 | %